Performance Evaluation Report (1 April, 2012  to March 31, 2013)  of RSCs i.e Institutions for the year 2012-13
Name of the Division : Crop Science
Name of the Institution : Directorate of Rapeseed-Mustard Research, Sewar, Bharatpur
RFD Nodal Officer : Dr. V.V.Singh

	S.No

	Objectives
	Weight
(%)
	Actions
	Success indicators
	Unit
	Weight
(%)
	Target/Criteria Value
	Achievements
	Performance
	Percent achievements against target values of 90 % column
	Reasons for shortfalls or excessive achievements, if applicable

	
	
	
	
	
	
	
	Excellent
	Very Good
	Good 
	Fair
	Poor
	
	
	
	

	
	
	
	
	
	
	
	100%
	90%
	80%
	70%
	60%
	
	Raw Score


	Weighted  score
	
	

	
	Genetic enhancement of rapeseed-mustard for higher productivity and its sustenance. 
	50
	Collection, characterization and evaluation of the germplasm


	No. of accessions acquired/collected


	Number


	5


	80


	70


	60


	50


	40


	95
	100
	5
	135.71
	This was the material received from various AICRP-RM centers and mostly advanced breeding lines. This is not a new collection from any area  

	
	
	
	Management of National Active germplasm of rapeseed-mustard
	No. of accessions evaluated


	Number


	7


	350


	325


	300


	275


	250


	450
	100
	7
	138.46
	More than 100 important trait specific lines were included in the evaluation progrmame hence number increased  

	
	
	
	Generation of genetic material.  

	Crosses attempted


	Number
	12
	100
	95
	90
	85
	80
	191
	100
	12
	201.05
	Because some new cross combination were suggested by IRC which was  held after submission of RFD  in June and August, 2012  


	
	
	
	Selection of promising entries in evaluation trials/heterotic   combination/transformation events
	Promising entries/heterotic combination generated


	Number
	12
	12
	11
	10
	9
	8
	12

(AICRP-RM)
	100
	12
	109.00
	

	
	
	
	Molecular profiling of promising trait specific lines


	Number of lines molecularly analyzed
	Number
	5
	50
	40
	30
	20
	10
	45

	95
	4.8

	112.5
	These 45 lines also include 5 check

	
	
	
	Truthful  label seed production 


	Truthful label seed produced
	Quintal
	9
	200
	180
	160
	140
	120
	272.85
	100
	9
	151.58
	49 quintal seed was also produced at farmers field 

	
	Increasing rapeseed-mustard productivity through ecologically sound and economically viable production and protection technologies
	24
	Cropping systems and input use efficiency/ 
Integrated pest management (disease, insect & weeds).

	Technology tested


	Number


	19


	6


	5


	3


	3


	2


	5
	90
	17.1
	100
	

	
	
	
	Identification of resistant/tolerant sources against biotic/abiotic  stresses
	Resistant sources identified
	Number


	5


	5
	4
	3
	2
	1
	4
	90
	4.5
	75
	

	
	Technology assessment and demonstrations 
	14
	On farm trials and technology demonstrations


	Technology demonstrated 

	Number

	9


	40


	35


	30


	25


	20


	50
	100
	9
	142.85
	10 FLDs were increased after the preparation of RFD on demand of famers and availability of fund

	
	
	
	Training to extension officers/farmers


	Training conducted  
	Number
	5
	10
	9
	8
	7
	6
	18
	100
	5
	200
	Due to sponsorship of ATMA and State department of agriculture, more training programmes  were conducted 

	
	Efficient functioning of RFD system
	3
	Timely submission of RFD 2012-2013


	On-time submission


	Date


	2


	Mar.23, 2012

	Mar.26, 2012

	Mar.27, 2012

	Mar.28, 2012

	Mar.29, 2012

	March 22, 2012
	100
	2
	100
	

	
	
	
	Timely submission of results 2012-2013


	On-time submission
	Date
	1
	May 1, 2013
	May 2, 2013
	May 3, 2013
	May 6, 2013
	May 7, 2013
	April 25,2013
	0
	0
	0
	

	
	Administrative reforms
	5
	Implementation of  ISO 9001
	Prepare ISO 9001 action plan
	Date
	1
	June 4, 2012
	June 5, 2012
	June 6 2012
	June 7, 2012
	June 8, 2012
	June 4, 2012
	100
	1
	100
	

	
	
	
	
	Implementation of ISO 9001 action plan
	Date
	2
	Mar. 25, 2013
	Mar. 26, 2013
	Mar. 27, 2013
	Mar. 28, 2013
	Mar. 29, 2013
	Certified on 18th January, 2013 by “WISS CERT PVT. LTD. 
	100
	2
	100
	

	
	
	
	Implementation  of mitigating strategies for reducing potential risk of corruption
	% of implementation
	%
	2
	100
	95
	90
	85
	80
	Implemented as per strategic plan
	0
	0
	0
	

	
	Improving Internal efficiency/responsiveness/service delivery of Ministry/Department
	4
	Implementation of sevottam
	Independent Audit of Implementation of Citizens’s charter Grievances
	%
	2
	100
	95
	90
	85
	80
	Citizen charter was followed
	0
	0
	0
	

	
	
	
	
	Independent Audit of Implementation of public grievance redressal system
	%
	2
	100
	95
	90
	85
	80
	No grievance was reported
	0
	0
	0
	


Total Composite Score: 90.4
Rating = Very Good

