Annual (April 1, 2013 to March 31, 2014) Performance Evaluation Report in respect of RFD 2013-2014 of RSCs i.e. Institutes
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	S.N
	 Objective(s)
	 Weight
	 Action(s)
	 Success Indicator(s)
	Unit
	 Weight
	Target / Criteria Value
	 Achievements 
	Performance
	Percent achievements against Target values of 90% Col.
	Reasons for shortfalls or excessive achievements, if applicable

	
	
	
	
	
	
	
	Excellent 100%
	Very Good 90%
	Good80%
	Fair 70%
	Poor 60%
	
	Raw Score
	Weighted Score
	
	

	1.
	Genetic enhancement and development of improved cultivars 
	50
	Evaluation of  genetic material  
	Breeding and germplasm lines evaluated 
	Number
	12
	765
	690
	612


	536
	459


	735
	96
	11.52
	106.5
	Availability of more germplasms from gene bank

	
	
	
	
	Entries tested under multi-location trials
	Number
	5
	155
	140
	124
	109
	93


	177
	100
	5.0
	126.4
	Breeding line with wide variation under multilocation trials during 2012-13 were repeated during the year.

	
	
	
	
	Lines identified for unique traits
	Number
	5
	12
	11
	10
	8
	7


	11
	90
	4.5
	100
	

	
	
	
	Development of improved cultivars
	Entries contributed for multi location trial
	Number
	5
	105
	95
	84
	74
	63


	140
	100
	5.0
	147.4
	Re-evaluation of some breeding strains and more strains identified for multi-location trials from AICRP-RM centres.

	
	
	
	
	Varieties identified for release
	Number
	5
	5
	4
	3
	2
	1


	4
	90
	4.5
	100
	

	
	
	
	Seed production programme 
	Breeder seed produced 
	Tonnes
	6
	14.5
	13.2
	11.6
	10.15
	8.7


	21.12
	100
	6.0
	160
	Cultivation of many recent varieties in minimum viable area resulted more production of breeder seeds. In addition the production depends on indent from DAC and SAU’s 

	
	
	
	
	Truthfully labelled seed produced


	Tonnes
	12
	32.5
	29.5
	26
	22.75
	19.5


	38.30
	100
	12.0
	129.8
	Special efforts has been made to produce more TFL seed to ensure quality seed to farmers.

	2
	Development and Identification of appropriate crop production and protection technologies
	21
	Development  of new technologies
	 New technologies tested
	Number


	11
	9
	8
	7
	6
	5


	10
	100
	11.0
	125
	Identification of more genotypes in AVT-I under normal sown conditions increased the number of technologies tested.

	
	
	
	
	 New technologies recommended
	Number
	10
	4
	3
	2
	1
	-


	7
	100
	10.0
	233.3
	Wide variation in weed flora across the OSB production zones resulted into generation of 5 different location specific weed control recommendations.

	3
	Technology dissemination and capacity building
	18
	Demonstrations conducted 
	 Frontline demonstrations conducted 
	Number
	10
	590
	531
	472
	413
	354


	597
	100
	10.0
	112.4
	Additional FLDs conducted by KVK-Bansur (Alwar) of this Directorate surpassed the targets.

	
	
	
	Farmers/ Extension officials training programmes organized 
	 Trainings  organized
	Number
	8
	7
	6
	5
	4
	3


	19
	100
	8.0
	316.7
	Extra efforts to train the farmers from non-traditional but potential areas under ATMA project resulted into 3-fold increase in target. 

	
	Efficient Functioning of the RFD system
	3
	Timely submission of Draft RFD           ( 2013-14) for approval
	On-time submission
	Date
	2
	May 15, 2013
	May 16, 2013
	May 17, 2013
	May 20, 2013
	May 21, 2013


	May 4, 2013
	100
	2.0
	100
	

	
	
	
	Timely submission of Results for RFD (2012-13)
	On-time submission
	Date
	1
	May 1, 2013
	May 2, 2013
	May 5, 2013
	May 6, 2013
	May 7, 2013


	April 27, 2013
	100
	1.0
	100
	

	
	Administrative Reforms
	4
	Implement ISO 9001 as per the approved action plan
	% Implementation
	%
	2
	100
	95
	90
	85
	80


	100
	100
	2.0
	100
	

	
	
	
	Prepare an action plan for innovation
	On-time submission
	Date
	2
	July 30, 2013
	Aug. 10, 2013
	Aug. 20, 2013
	Aug. 30, 2013
	Sept. 10, 2013


	July 23, 2013
	100
	2.0
	100
	

	
	Improving internal efficiency/responsiveness/service delivery of Ministry/ Department
	4
	Implement Sevottam
	Independent audit of implementation of Citizen’s Charter
	%
	2
	100
	95
	90
	85
	80


	100
	100
	2.0
	100
	

	
	
	
	
	Independent audit of implementation of public grievance redressal system
	%


	2
	100
	95
	90
	85
	80


	100
	100
	2.0
	100
	


Total Composite Score: 98.52 
Procedure for computing the Weighted and Composite Score









    Rating: Excellent
1. Weighted Score of a Success Indicator = Weight of the corresponding Success Indicator x Raw Score / 100

2. Total Composite Score = Sum of Weighted Scores of all the Success Indicators

