Annual (April 1, 2014 to March 31, 2015) Performance Evaluation Report in respect of RFD 2014-2015 of DRMR
Name of the Division: 
Crop Science 
Name of the Institution: 
Directorate of Rapeseed-Mustard Research
RFD Nodal Officer of the RSC: 
Dr. V.V.Singh
	S.No.
	 Objective(s)
	 Weight
	 Action(s)
	 Success Indicator(s)
	 Unit
	 Weight
	Target / Criteria Value
	 Achievements 
	Performance
	Percent achievements against Target values of 90% Col.
	Reasons for shortfalls or excessive achievements, if applicable

	
	
	
	
	
	
	
	Excellent 100%
	Very Good 90%
	Good%
	Fair 70%
	Poor 60%
	
	Raw Score
	Weighted Score
	
	

	1.
	Utilizing frontier research for better exploitation of genetic resources
	32
	Collection, characterization and conservation of genetic resources  
	Germplasm  and breeding lines evaluated/ characterized 
	Number
	8
	840
	700
	560
	420
	280
	794


	96.7
	7.74
	113.4
	Supply of more germplasm from gene bank

	
	
	
	
	Germplasm collected/ lines identified for unique traits 
	Number
	4
	12
	10
	8
	6
	4

	15

	100
	4
	150.0
	Conditions were favourable for identification of more genotypes

	
	
	
	Evaluation of genetic resource for suitable crop husbandry practices
	Germpalsm/ breeding lines evaluated 
	Number
	5
	170
	142
	114
	86
	58
	144


	90.07
	4.50
	101.4
	-

	
	
	
	Development of improved varieties suited for diverse agro-ecologies
	Varieties identified by  AICRP-RM varietal identification committee
	Number
	5
	5
	4
	3
	2
	1

	3


	80
	4.00
	75.0
	-

	
	
	
	Seed production programme 
	Breeder seed produced 
	Tonnes
	4
	16.0
	13.3
	10.6
	7.9
	5.2

	21.33


	100
	4
	160.4
	A surplus of 11.8 tonnes over DAC indent was already available

	
	
	
	
	Truthfully labeled seed produced


	Tonnes
	6
	42.0
	35.0
	28.0
	21..0
	14.0


	41.70


	99.57
	5.97
	119.1
	Quality seed production programme of wheat was included 

	2.
	Development and Identification of appropriate production-protection technologies
	24
	Identification/development /testing of new technologies/methods
	Technologies/methods/practices  evaluated for improving soil health, land use and input  use efficiencies
	Number


	9
	8
	7
	6
	5
	4

	7


	90
	8.10
	100.0
	-

	
	
	
	
	 Technologies/methods/practices evaluated for effective management of biotic stresses (insect pest diseases, weeds)
	Number
	9
	5
	4
	3
	2
	1
	4

	80
	7.20
	100.0
	-

	
	
	
	Technology refinement for different agro-ecologies
	Technology/methods/practices recommended
	Number
	6
	6
	5
	4
	3
	2


	6

	100
	6
	120.0
	-

	3
	Capacity building and knowledge management through technology assessment, refinement and dissemination
	24
	Capacity building for technology application 
	 On Farm Trials/ Front line demonstrations conducted 
	Number
	8
	678
	565
	452
	339
	226

	493


	83.62
	6.69
	87.35
	-

	
	
	
	
	 Trainings  organized (farmers, rural youths, women and in-service extension persons)
	Number
	6
	20
	16
	12
	8
	4


	30

	100
	6
	187.5
	Additional funds were provided  by different agencies

	
	
	
	Partnership development including licensing of DRMR technologies 
	Partners  identified
	Number
	3
	5
	4
	3
	2
	1
	8

	100
	3
	200.0
	Due to visibility of Directorate more partners came forward

	
	
	
	Knowledge dissemination
	Print and electronic publication products brought out 
	Number
	3
	16
	13
	10
	7
	4
	14


	93.3
	2.80
	107.7
	-

	
	
	
	
	Kisan Mela/Kisan Gosthi/Radio or TV Krishi Shiksha programme organized attended
	Number
	4
	19
	16
	13
	10
	7
	21


	100
	4
	131.3
	More funds were provided  by different agencies

	
	Publication/ Documentation
	5
	Publication of the research articles in the journals having the NAAS rating of 6.0 and above
	Research articles published
	No.
	3
	9
	8
	6
	4
	3
	12


	100


	3
	150.0
	Papers published according to the research mandate

	
	
	
	Timely publication of the  Institute Annual Report (2013-2014)
	Annual Report published
	Date
	2
	30.06. 2014
	02.07. 2014
	04.07. 2014
	07.07.2014
	09.07.2014
	18.06.2014
	100
	2
	-
	-

	
	Fiscal resource management
	2
	Utilization of released plan fund
	Plan fund utilized
	% 
	2
	98
	96
	94
	92
	90
	99.60


	100


	2
	-
	-

	
	Efficient Functioning of the RFD system
	3
	Timely submission of Draft RFD  2014-15 for approval
	On -time submission
	Date
	2
	May 15, 2014
	May 16, 2014
	May 19, 2014
	May 20, 2014
	May 21, 2014
	-
	0
	0
	-
	-

	
	
	
	Timely submission of Results  for  2013-14
	On- time submission
	Date
	1
	May 1, 2014
	May 2, 2014
	May 5, 2014
	May 6, 2014
	May 7, 2014
	April 22, 2014
	100
	1
	-
	-

	
	Enhanced Transparency/ Improved Service delivery of Ministry/Department
	3
	Rating from Independent Audit of implementation of Citizens’/ Clients Charter (CCC)
	Degree of implementation of commitments in CCC
	%
	2
	100
	95
	90
	85
	80
	96


	92

	1.84
	100
	-

	
	
	
	Independent Audit of implementation of  Grievance Redress Management (GRM) system
	Degree of success in implementing GRM
	%
	1
	100
	95
	90
	85
	80
	100


	100


	1
	100
	-

	
	Reforming Administration
	7
	Updated departmental strategy to align with revised priorities
	Date
	%
	2
	Nov.1, 2014
	Nov.2, 2014
	Nov.3, 2014
	Nov.4, 2014
	Nov.5, 2014
	Oct. 2, 2014
	100
	2
	100
	-

	
	
	
	Implement agreed milestones of approved Mitigating Strategies for Reduction of potential risk of corruption (MSC)
	% of  implementation 
	%
	1
	100
	90
	80
	70
	60

	100


	100


	1
	100
	-

	
	
	
	Implement agreed milestones for implementation of ISO 9001
	% of  implementation
	%
	2
	100
	95
	90
	85
	80


	100


	100


	2
	100
	-

	
	
	
	Implement agreed milestones of approved Innovation Action Plans (IAP)
	% of  implementation
	%
	2
	100
	90
	80
	70
	60

	100


	100


	2
	100
	-


Total Composite Score: 91.84
Rating : Very Good

Annexure -1

Actual Scientific Staff in position in the Institute and their research articles publications published in International and National Journals having NAAS rating 6.00 or more during April 1, 2014-March 31, 2015
Name of the Division: 
Crop Science 

Name of the Institute: 
ICAR-Directorate of Rapeseed-Mustard Research

	S.No.
	Category of scientific Staff 
	Actual Scientific Staff in position (Nos.)
	Research articles publications as first/ corresponding author (Nos.) 
	Publication productivity (Number of research articles publications divided by number of Scientists)

	1.
	Principal Scientist
	06
	04
	0.67

	2.
	Senior Scientist
	07
	04
	0.57

	3.
	Scientist
	11
	04
	0.36

	
	
	24
	12
	0.50


